## Schedule
EXHIBIT D
Project Schedule
Charter Name:
School Type (Grades):
Activity Name |  | Duration | Start | Finish
SITE SELECTION/ACQUISITION
IZ005 | Site Selection
IZ040 | Acquisition Analysis
IZ900 | Preferred Site Selected
IZ070 | Escrow
Demolition
DEPT. OF TOXIC SUBSTANCES CONTROL
Phase I
DTSC PEA
DTSC RAW / RAP
NFA issued by DTSC
CALIF. ENVIRON. QUALITY ACT
Initial Study Initiation
CEQA Determination MND Vs. EIR
Board Approval of CEQA (EIR)
UTILITIES NEW SERVICE REQUESTS
Utilities Relocation and/or New Service
DESIGN
Architect NTP
Schematic Design
Design Development
Construction Documents
Division of State Architect (DSA)
B Permit Approval Process
BID/AWARD
Bid
Award
CONSTRUCTION
Construction
Date of Construction NTP
Construction
Substantial Completion
Final Construction Contract Completion
B-Permit/ Off-Site - Construction
Construction - B Permit Work
Inspection Signoff - B Permit Work
SCHOOL OPENING
F&E / Punch List / OEHS Final Clearance
School Occupancy