## Fulton-Transformation
SIG Form 10.2 - Transformation Implementation Chart for a Tier I or Tier II School
LEA: | Los Angeles Unified School District |  |  | Date: May 20, 2016
School: | Robert Fulton College Preparatory School
Required Components | Strategies |  |  | Start & End Dates (MM/YYYY) | Oversight | Description of Evidence
II-SIG 10: Replace the principal who led the school prior to the commencement of the transformation model.
Principal Replacement* | Raquel George was hired within the last 2 years and has the experience and skills needed to implement a successful transformation model. She has already led the school community through a LAUSD reform process and WASC self-study, successfully. Principal George has already established positive school-wide relationships and stakeholders have confidence in her ability to collaboratively lead the school and increase student achievement. Year 1: Completed Year 2: Will continue Completed Year 3: Will Continue |  |  | July 1, 2014 - June 2017 | LAUSD ISIC ESC Local District Staff | WASC Visit 2012 Public School Choice 4
Principal name | Raquel George | Hire date | 2014-07-01
*LEAs that retain a principal hired within the last 2 years should be able to demonstrate that: (1) the prior principal in the school at issue was replaced as part of a broader reform effort, and (2) the new principal has the experience and skills needed to implement successfully a turnaround, restart, or transformation model.
II-SIG 11: Use rigorous, transparent, and equitable evaluation systems for teachers and principals that take into account data on student growth as a significant factor that are designed and developed with teacher and principal involvement.
Principal and teacher involvement | In April 2009, the LAUSD Board of Education passed a resolution calling for the creation of a Teacher Effectiveness Task Force (TETF) to examine successes and challenges related to employee performance and development. The TETF, including educators, labor representatives and parents, made recommendations in five connected areas: evaluation, support mechanisms, tenure, differentiated compensation, and legislation. These recommendations called for a more meaningful performance review system that is tightly aligned to professional development available to educators, which informs a broader talent development/human capital framework. In 2010-11, components of the new evaluation system (called Educator Growth and Development Cycle, "EGDC") were developed for SIG Cohort 1 schools. SIG teachers and administrators provided feedback on the Teaching and Learning Framework, School Leader Framework, the professional develoment trainings, and stakeholder surveys. This feedback from SIG principals and teachers informed the 2011-12 Initial Implementation Phase (IIP) of the new teacher evaluation system, which was a voluntary pilot of the new formal observation system in 47 schools across the District. In turn, the feedback from IIP participants helped inform the district-wide pilot of TGDC (Teacher Growth and Development Cycle) in 2012-13, in which all district schools each had at least 1 administrator and teacher going through an observation cycle and giving feedback on the process. By 2013-14, the District implemented TGDC district-wide in lieu of the old evaluation system as well as piloted the School Leader Growth and Development Cycle with over 60 principals. The Talent Management Division, which oversees EGDC implementation, will continue to collect feedback from teachers and administrators. For 2015-16 the Office of Professional Learning and Leadership Development will oversee the evaluation system, which is now entitled Educator Development and Support : School Leaders and Teachers Year 1: Will continue Completed Year 2: Will continue Completed Year 3: Will continue |  |  | 8/2011 - 6/2017 | Chief, Division of Intensive Support and Intervention; Executive Director, Talent Management For 2015-16 - Academic Officer, Office of Curriculum, Instruction and School Support ;Chief, Professional Learning and Leadership Development | Talent Management Website Teacher Effectiveness Task Force Report Feedback surveys and reports Training materials and presentations SIG MOUs For 2015-16: Professional Learning and Leadership Website, Feedback surveys and reports; Training materials and presentations My Professional Growth System (MyPGS) My Professional Growth System is the District’s web-based technology platform used to provide regular evaluation documentation for educators being evaluated.
Data on student growth | In 2011, the District unveiled its new Academic Growth over Time system of measuring student learning gains in order to help teachers and administrators understand how much progress individual students have made on standardized tests from one year to the next. AGT is based on a value-added approach that controls for a student’s performance from the prior year, along with information about external factors that often influence test results, to compute expected performance. This provides a more complete picture of student learning because AGT compares a student's actual performance to his or her expected performance, giving us a sense of the growth made in addition to expected learning gains in a given year. AGT also allows educators to examine the impact of schools and educators on students’ learning outcomes by combining the value-added results for groups of students in the same classrooms and schools. The Board of Education and the Superintendent have been committed to the selection of the most relevant and accurate statistical model to compute school-level AGT results for use by our schools and educators. AGT results represent one piece of useful data that has helped deepen understanding of the complex picture of student learning. Once the State's accountability system has made the shift to using Common Core-aligned assessments, AGT will follow suit. In addition, LAUSD is part of the CORE Waiver consortium through which participating LEAs have committed to including at least one signficant component of teacher and principal evaluations based on a measure of student academic achievement and growth. For 2015-16, as detailed in the teacher’s contract, the applicable record of student progress and achievement comprised of individual SBAC, school-level Academic Growth over Time (AGT) and various non-SBAC-based multi-measure data sources are to be considered a significant but limited part of the overall performance evaluation rating. For principals, the LAUSD-AALA MOU states that the evaluation process allows for review, discussion, and incorporation of school wide standards-based student achievement data and that additional data may be used. Year 1: Will continue Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Started 8/2011 Aug 2014 – June 2017 | Executive Director, Data and Accountability; Director, Performance Management | AGT website CORE Waiver application Board reports and informatives Training materials and presentations My Professional Growth System (MyPGS)My Professional Growth System is the District’s web-based technology platform used to provide regular evaluation documentation for educators being evaluated.
Multiple observation-based assessments | At the heart of the District's Educator Growth and Development Cycle is a multiple measures evaluation system comprised of Observation of Practice, Stakeholder Feedback, Contributions to School Community, and Contributions to Student Learning Outcomes, all based on our Teaching and Learning and School Leader Frameworks. Observation of Practice is the largest component of the evaluation process and involves multiple cycles of collecting objective, qualitative data, tagging and scoring the data according to rubrics, and conducting coaching conversations to identify areas of strength and growth. Stakeholder feedback collects data from students, parents, and teachers on classroom and school climate. Contributions to Student Learning Outcomes takes into consideration various measures of student performance, including but not limited to Academic Growth over Time. And lastly, Contributions to School Community acknowledges the impact that teachers and administrator have on students beyond instruction and the classroom. For 2015-16 the evaluation process for educators will include multiple observations conducted by trained and certified observers using the Teaching and Learning Framework (TLF) and the School Leadership Framework (SLF), both aligned to the California Standards for the Teaching Profession. Evidence is scripted in the district’s My Professional Growth System (MyPGS) platform that includes a coordinated reflection on practice and actionable feedback. Educators meet with supervisors to receive feedback on practice and to discuss strategies to improve student Year 1: Will continue Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Started 8/2011 Aug 2014 – June 2017 | Chief, Division of Intensive Support and Intervention; Executive Director, Talent Management For 2015-16 - Academic Officer, Office of Curriculum, Instruction and School Support ;Chief, Professional Learning and Leadership Development | Talent Management website Board reports and informatives Training materials and presentations For 2015-16 : Professional learning and Leadership Development website Board reports and informatives Training materials and presentations My Professional Growth System (MyPGS)My Professional Growth System is the District’s web-based technology platform used to provide regular evaluation documentation for educators being evaluated
Ongoing collections of professional practice | The District is using MyPGS (My Professional Growth System) by True North Logic to help manage the evaluation process and provide a platform for teachers to develop a portfolio of professional practice so they can track their own professional growth over time. Because teacher evaluation is just one side of the Educator Growth and Development Cycle, the District has also started to pilot in 2013-14 a learnig management system called My Personalized Learning Network (MyPLN) for teachers to share best practices and seek professional development that is tailored to their individual needs and interests. Year 1: Completed Year 2 : Will continue Completed Year 3: Will continue |  |  | Started 8/2011 Aug 2014 – June 2017 | Chief, Division of Intensive Support and Intervention; Executive Director, Talent Management; Executive Director, Human Capital Initiatives For 2015-16 - Academic Officer, Office of Curriculum, Instruction and School Support ;Chief, Professional Learning and Leadership Development | Talent Management Website Human Capital Initiatives Website MyPGS Website MyPLN Website
II-SIG 12: Identify and reward school leaders, teachers, and other staff who, in implementing this model, have increased student achievement and high school graduation rates; and identify and remove those who, after ample opportunities have been provided for them to improve their professional practice, have not done so.
Identify and reward | We will create a plan/system to provide monetary incentives for teachers and administrators who participate in professional development and delivery of PD. Compensate teachers and administrators who facilitate/present at a conference. During the SIG PD days, 6 teachers were compensated for presenting sessions to their colleagues. Teachers are evaluated using LAUSD's Teacher Growth and Development Cycle. Teachers are observed 4-6 times a year and have 6-8 one-on-one meetings with adminstrators to review lessons plans and student achievement data. At the end of each semester teachers are evaluated using the Teaching and Learning Framework. Teachers who received a low mark in any area are expected to show growth in the following semester. Teachers who continue to receive low marks are then referred to the Peer Assistance and Review Team to provide additional support to teachers. Compensate staff that participates in the Lesson Study Model (collaborative design lessons, observe, reflect and refine). Recognize teachers who plan and implement activities that promote college and career readiness. Plans will include recognizing at Faculty and Parent Meeting. We will also create an employee of the month wall to begin with small celebrations. Recognize teachers with perfect attendance monthly. Pay fees for teachers to join professional organizations / professional publication subscriptions. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Aug 2014 – June 2017 | Local dDstrict Director; Principal; APs; Coordinators; Dept. Chairs 2015-16: Local District Superintendent and Director | Incentive Plan Document Agendas Sign-ins PD Plan
Opportunities to improve professional practice | Compensate staff that attends professional development workshops beyond school hours and on Saturdays, such as Marzano’s instructional strategies, Kagan’s cooperative learning/student engagement, authentic literacy, and PLCs. The Reed Investment Grant allowed us to monetarily reward teachers who attended additional PD outside of normal works hours. Teachers were compensated at their hourly rate to attend 20 hours of professional development after-school and on Saturdays. The PD focused on analyzing nonconventional data. In addition, teachers participated in the planning and presentation of the PD. The Reed Investment Grant also pays for 3 teacher mentors to provide support to new and struggling teachers. Three model teachers were chosen to provide support for select teachers throughout the school year. Compensate staff that participates in the lesson study model (collaborative design lessons, observe, reflect and refine). Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Aug 2014 - June 2017 | Local District Director; Principal; APs; Coordinators; Dept. Chairs | Agendas; Sign-ins; Observation tools; Observation data; Lesson Plans; Reflections; Pacing Plan; Curriculum Maps; Common Formative Assessments; Common Summative Assessment;
Identify and remove | To measure teacher effectiveness, teachers will be expected to implement the identified and agreed-upon research-based instructional strategies. Classroom observations will be used as a qualitative measure of teacher effectiveness in using the strategies. AP Class pass rate is used to determine placment of teachers in those classes. Teachers who have met or exceed the district average for AP pass rate stay in those positions. Those who do not are provided with opportunities to attend additional PD in their content area. Teacher effectiveness is also measured by the percentage of fails they give to their students at the end of each semester. Teachers with high fail rates undergo a detailed gradebook check and are required to present their grading methods and lesson design. Administration will also provide opportunities for growth throughout the year by having the teachers participate in the rigorous TGDC process. The school will follow the LAUSD-UTLA contract regarding teacher evaluations. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Jun 2015 - Jun 2017 | Principal; Assistant Principals | PD Sign-ins Class Observation Attendance Roster
II-SIG 13: Implement strategies that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the transformation school.
Recruitment | Fulton CP stakeholders will collaboratively ensure that our hiring and staffing is aligned to our mission and vision of having students be college-prepared and career-ready. A hiring committee composed of an administrator, coordinator, teachers, and parent community representative will conduct all interviews and collaboratively make hiring recommendations to the principal. The hiring and staffing of teachers will be dictated primarily by student need to ensure we provide all core and A-G courses, and intervention courses that address all student needs, including English Learners and students with disabilities. Through this process, we will only accept highly qualified teachers who embrace our mission and vision and want to work with our students. We will recruit candidates by: • Posting vacancies on the district and school websites with a brief description of the ideal candidate • Attending District job-fairs • Connecting with District and University teaching programs • Networking with currently credentialed teachers by content area Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Mar 2014 – Jun 2017 | Principal; Assistant Principal; ISIC ESC Local District Director, Superintendent | Job Flyers Job Description Online Postings
Placement | Placement of teachers will be based on improving our ability to address our three urgent needs (college/career readiness, data-driven accountability, and collaboration): • School-wide goals and Student program needs • Teacher preference • Department chair / administrator recommendation • Teacher Credential / NCLB requirements Year 1: Started Completed Year 2: Will contine Completed Year 3: Will continue |  |  | May 2014 – June 2017 | Principal; Assistant Principal; ISIC ESC Local District Director, Superintendent | Master Schedule; Preference Sheets; Master Schedule Meeting w/ILT & agenda; Agenda; Sign-ins; Teacher Credentials
Retention | We will: • Provide paid leadership and growth opportunities for teachers in curriculum planning, instructing, mentoring, and coaching • Refine our systems of collaboration by providing teachers time and resources to focus on teaching and learning together. • Encourage and provide opportunities for teachers to participate in decision-making. • Celebrate successes Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Spring 2014 – June 2017 | Principal; APs; Coordinators; Dept. Chairs; Mentor Teachers | Agendas; Assemblies; Stipend; Duties as Assigned; Announcements; Marquee; Newsletter; Pacing Plan; Curriculum Maps; Common Formative Assessments; Common Summative Assessment; Reflections
II-SIG 14: Provide staff ongoing, high-quality, job-embedded professional development that is aligned with the school's comprehensive instructional program.
| To address the three urgent needs (College and Career Readiness, data-driven accountability, and a system of collaboration) our staff will participate in high quality and job-embedded professional development aligned with the school’s instructional program (see below). Fulton staff will have time beyond the regular school calendar to plan the implementation of effective instructional strategies in the intervention and enrichment programs at the beginning of the semester (4 days, 6hrs a day). In addition , staff will participate in PD workshops on Saturdays, that focus on Cooperative Learning, Student Engagement, Authentic Literacy, and Marzano's strategies. Staff will also have increased collaboration time (1,080 minutes a year) to meet with PLC members to develop common lessons that embed identified strategies (Marzano, Cooperative Learning, Authentic Literacy) and develop common assessments. Collaboration time will increase by 40 minutes once a week on Tuesdays, throughout most of the year. Urgent Need: College and Career Readiness Cooperative Learning - Our school has already trained 50% of our faculty in Kagan’s cooperative learning strategies, and many teachers have begun integrating cooperative learning activities into their instruction. We will continue to support implementation of the strategies by providing additional Kagan trainings in grades 6-12. Frequent classroom observations and timely feedback will ensure effective differentiation. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Spring 2013 (began) To June 2017 | Local District Director; Principal; APs; Coordinators; Dept. Chairs; Teacher Mentors; Teachers; PLCs | Agendas; Sign-ins; Class Observations; Lesson Plans; PD Feedback and Reflections;
| Authentic Literacy - The use of authentic text, which is aligned with the new Common Core state standards, will create meaningful reading and writing experiences for students in all content area classrooms. We will expand the integration of authentic literacy, including reading and writing about informational and procedural text, across all content areas. • Provide authentic literacy PD to our staff • Provide on-going CCSS PD to our staff (Karen Patino) • Provide PD around the writing process to support CCSS • Provide a two-day ERWC training to create awareness of how CSU defines students’ ELA skill level as college ready • Provide PD on use of technology to engage students in teaching and learning. • Provide PD around student engagement to support ELs and students with disabilities (Kate Kinsella) • Provide PD registration fees for staff members to attend off-site professional development around student engagement Identifying Similarities and Differences - We will teach students to compare, classify, and create metaphors/analogies in identifying similarities and differences (Marzano). This strategy supports the EL Master Plan, which states that EL students must be provided with access to well-articulated, standards-based core curriculum via many different scaffolding techniques and strategies. • Provide Marzano PD on identifying similarities and differences. • Provide PD on using graphic organizers to scaffold instruction and gradually release • Provide PD on implementing the Gradual Release of Responsibility Model • Provide PD on calibrating rigor in lessons and lesson objectives Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Spring 2013 (began) To June 2017 | Local District Director; Principal; APs; Coordinators; Dept. Chairs; Teacher Mentors; Teachers; PLCs | Agendas; Sign-ins; Class Observations; Lesson Plans; PD Feedback and Reflections;
| Numeracy - The focus on numeracy will encourage multiple representations of problems and solutions to support the English language development and mathematical needs of English Learners who may not understand the academic vocabulary. Provide PD to administrators on numeracy and its use in grade 6 math classes Urgent Need: Data-Driven Accountability and Collaboration Professional Learning Communities - We will focus on learning rather than teaching, work collaboratively, and will hold ourselves accountable for results. • Train staff on the PLC process, development of SMART goals, and the use of common formative and summative assessments. Through the PLC process, teachers will work collaboratively to create on-going measures to check for student understanding on daily/weekly basis (ie. Exit slips, learning logs, presentations, writing samples) to provide tier 1 intervention, as needed. • Provide PD registration fees for teachers to attend off-ste professional development around PLCs • Provide PD on targeted data-driven intervention and enrichment Instructional Rounds - Provide the Instructional Leadership Team and selected core teachers training on Instructional Rounds and its connection to the Teaching and Learning Framework. The Instructional Rounds process will enhance teachers’ pedagogical skills and develop a culture of collaboration. Teachers will have the opportunity to observe one another and compare their own practices with those observed. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | Spring 2013 (began) To June 2017 | Local District Director; Principal; APs; Coordinators; Dept. Chairs; Teacher Mentors; Teachers; PLCs | Agendas; Sign-ins; Class Observations; Lesson Plans; PD Feedback and Reflections;
II-SIG 15: Give the school sufficient operational flexibility (such as staffing, calendars/time, and budgeting) to implement fully a comprehensive approach to substantially improve student achievement outcomes and increase high school graduation rates.
| Calendars/Time: Extended Day for all teachers and certificated support staff (coordinators, librarian), some SPED paraprofessionals, to provide intervention and enrichment to all students. Staffing: Teachers in ELA and Math to support Long term English Learners and at-risk students through targeted instruction and to provide credit recovery classes to students in order to complete A-G requirements. Staffing: Teachers in Music and Art to provide academic enrichment classes to middle school students who do not have access to such electives due to recent RIFs and the need for district intervention classes. Staffing: PSA to support the socio-emotional needs of our students through supplementary services. Year 3: PSA will be changed to PSW based on needs. Staffing: The Instructional Specialist duties replaced by Assistant Principal (AP) will supervise and monitor the instructional program, specifically ELA and math, so that teachers receive the development, support and guidance to ensure targeted student population academic achievement; plan professional development activities and provide intensive instructional support to teachers on implementation of professional development / instructional strategies; lead teachers and assist the principal to ensure that the professional development plan and intervention services are aligned with the Single Plan for Student Achievement and address the linguistic and academic needs of English Learners, and the academic needs of low-income students and students with disabilities; and facilitate grade-level team/department meetings to analyze assessment data, review student work, debrief classroom observations and best practices, identify student needs, and plan differentiated instruction. Year 1: Started. PSA funded thru a different funded source Year 2: Will Did not continue the position of Instructional Specialist , the duties will be assumed by an Assistant Principal funded by Categorical and LCFF Funds Year 3: Will continue. Switched the PSA position to a PSW to support the needs of our students. |  |  | July 2014 – June 2017 | Principal; APs; SAA; Coordinator | Payroll Staff Roster Services Provided Bell Schedule Master Schedule
| Staffing: Intervention Coordinator will monitor students to provide early identification and intervention of at-risk students; participate in and/or facilitate multidisciplinary intervention teams such as Student Success Team, Coordination of Services Team, and Discipline Review Team, to provide coordinated support and intervention; provide individual and group guidance to students in the academic, and socio-emotional domains; assist teachers in the use of student-centered data to organize structures for instruction and intervention to ensure all students achieve at high levels; provide parent education workshops. The coordinator will be paid 3 hr from Title 1 and 3 hrs, 5 days a week from SIG. Staffing: Provide Counselor X-time to meet with parents and students to support completion of A-G requirements and graduate college ready. To increase parent participation, meeting Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | July 2014 – June 2017 | Principal; APs; SAA; Coordinator | Payroll Staff Roster Services Provided Bell Schedule Master Schedule
| Staffing: Administrator X-time for supervision of certificated staff participating and leading intervention and enrichment activities beyond the regular school day and on Saturdays to support students in meeting their A-G requirements: Tutorial Services, Counselor/Student/Parent conferences, Parent Meetings. Custodial / Clerical Overtime and Campus Aide OT to provide services during the extended learning time. Staffing: Teacher Assistants to support students in the core and intervention classes. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | July 2014 – June 2017 | Principal; APs; SAA; Coordinator | Payroll Staff Roster Services Provided Bell Schedule Master Schedule
II-SIG 16: Use data to identify and implement an instructional program that is research-based and vertically aligned from one grade to the next as well as aligned with California's adopted academic standards.
Develop screening criteria | In the event that a grade-level team of teachers wants to implement a new instructional program for core, intervention or enrichment purposes, they will submit a proposal to their department chair and ILT for review. The proposal will be based on school and student data that illustrates a need for the program. It must also be research-based and aligned to one of the three urgent issues (college/career readiness, data-driven accountability, and collaboration). All team members must commit to implement the program with fidelity. The ILT will evaluate the program based on a set criterion. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | August 2014 – June 2017 | Principal; APs; Dept. Chairs; Coordinators | Agendas; Sign-ins; PD Calendar; Developed Tools
Evaluate research base and alignment of current program | On a quarterly basis, the ILT will analyze school-wide data and share the results with the school community to determine if we have met our SMART goals through the implementation of current core, supplemental enrichment and intervention programs. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | August 2014 – June 2017 | Principal; APs; Dept. Chairs; Coordinators; Teachers; Governance Councils | Agendas; Sign-ins; PD Calendar; Developed Tools
Identify a new instructional program or revise current program | Teachers and PLCs will use their student data results to determine effectiveness of the core, intervention, and enrichment supplemental programs. Teachers and PLCs will collaborate with the department members, supervising administrator and ILT to identify and screen possible new instructional programs for enrichment and intervention or revise existing programs. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | August 2014 – June 2017 | Principal; APs; Dept. Chairs; Coordinators; Teachers | Agendas; Sign-ins; Program Materials; Student Work/data
Implement new or revised instructional program | If a new program is implemented or revised, teachers will receive support to ensure it’s implemented with fidelity. Implementation and student performance results will be monitored by the department chair/administrator and ILT. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | August 2014 – June 2017 | Principal; APs; Dept. Chairs; Coordinators; Teachers | Agendas; Sign-ins; Program Materials; Lesson Plans; Classroom Observations; Student Work/data
II-SIG 17: Promote the continuous use of student data to inform and differentiate instruction in order to meet the academic needs of individual students.
| The use of assessments will be an integral part of the daily instructional process. We will use assessments as sources of information for both students and teachers by developing high-quality common formative and summative assessments. These assessments will guide improvements in the ongoing teaching and learning context (assessments for learning), measure the level of success or proficiency that students obtain at the end of an instructional unit, and monitor college-preparedness and career readiness among all students. In PLCs, teachers will use the school-wide S.M.A.R.T. goals to guide the development of their PLC’s instructional S.M.A.R.T. goals. They will use MyData to examine student achievement data, identify at-risk students, and analyze early warning data to inform instruction and monitor student learning. Teachers will have access to comprehensive history reports to examine students’ longitudinal learning patterns. Teachers will use this data to make decisions on teaching strategies, project-based learning experiences, interventions, and enrichments. As a result, they will conduct ongoing Tier 1 progress monitoring. Provide instructional software to support the math and ELA intervention and enrichment classes. Software will include ALEKS for grade 6 math support, Vantage Learning for writing in grades 7 and 8, and Revolution 360 CAHSEE Support. To support the increased class time, we will select and purchase supplemental materials to support the needs of intervention, and enrichment courses such as math manipulatives, and math journals for students to develop comprehension and writing through authentic literacy activities. Technology - To support the increased class time and embed technology skills in the curriculum we will select and purchase technology to meet the needs of the intervention and enrichment courses. Some classes will need a cluster (5) of desk-top computers to offer differentiation opportunities (instructional software in math and ELA. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | August 2014 – June 2017 | Principal; APs; Dept. Chairs; Coordinators; Teachers | Agendas; Sign-ins; Common Formative Assessments; Common Summative Assessments; LAUSD Periodic Assessment; Student Work/data
| Provide instructional software to support the math and ELA intervention and enrichment classes. Software will include ALEKS for grade 6 math support, Vantage Learning for writing in grades 7 and 8, and Revolution 360 CAHSEE Support. To support the increased class time, we will select and purchase supplemental materials to support the needs of intervention, and enrichment courses such as math manipulatives, and math journals for students to develop comprehension and writing through authentic literacy activities. Technology - To support the increased class time and embed technology skills in the curriculum we will select and purchase technology to meet the needs of the intervention and enrichment courses. Some classes will need a cluster (5) of desk-top computers to offer differentiation opportunities (instructional software in math and ELA. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | July 2014 – June 2017 | Principal; APs; Dept. Chairs; Coordinators; Teachers | Purchase Orders; Lesson Plans; Increased Student Achievement; Screening by ILT; Classroom observations
II-SIG 18: Establish schedules and implement strategies that provide increased learning time.
| Increase by Day | Increase by Week | Increase by Year
Core - Core Classes will include credit recovery opportunities in ELA, math, science, and social studies to all students so that they meet the A-G graduation requirements, especially at-risk and LTEL students. for to at-risk and LTEL students, as needed,to meet the A-G requirements. The additional instructional minutes will provide time to add a 7th period class. Year 1: Started Completed Year 2: Will Continue Completed Year 3: Will continue | 40 min | 160 min by the week (27 wks) = 4320 plus 440 additional yearly minutes due to 11 non-Collaboration Days | 4320 + 440 4760 Total | August 2014 – June 2017 | Principal; AP; Certificated Staff; Classified Staff | Master Schedule Bell Schedule Payroll
Enrichment The enrichment classes will provide academic elective classes to all middle school and high school students who may not have access to such electives due to recent RIFs and the need for district intervention classes. Year 1: Started Completed Year 2: Will Continue Completed Year 3: Will continue | 40 min | 160 min by the week (27 wks) = 4320 plus 440 additional yearly minutes due to 11 non-Collaboration Days | 4320 + 440 4760 Total | August 2014 – June 2017 | Principal; AP; Certificated Staff; Classified Staff | Master Schedule Bell Schedule Payroll
Collaboration - Staff will have increased collaboration time (1,080 minutes a year) to meet with PLC members to develop common lessons that embed identified strategies (Marzano, Cooperative Learning, Authentic Literacy) and develop common assessments. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  | 40 min a week (27 weeks total) | 1080 (on Tuesdays) | August 2014 – June 2017 | Principal; AP; Certificated Staff; Classified Staff | Master Schedule Bell Schedule Payroll Sign-ins Agendas
Total Unduplicated Time | 40 min/day | 200 min/week | 5840 min/year
II-SIG 19: Provide ongoing mechanisms for family and community engagement.
| To better meet the needs of our working families, we will hold morning and evening meetings to personally continue engaging in dialogue with parents and community members about our school program. The meetings will be held in both Spanish and English to support our predominately Spanish-speaking families. We will hold a minimum of four parent meetings per month.Meetings formats will include: • Governance Councils such as School Site Council and School Based Management, English Learner Advisory Council. • Coffee with the Principal • Athletics Parent Meetings • Academic Events • Parent Conferences • Back to School Night • College-Bound Workshops • Grade 6 and 9 Articulation We will also use multiple methods of communication to reach the maximum number of parents: • Quarterly Newsletter – English/Spanish • School Website • College Center Newsletter • Blackboard Connect • Marquee Provide Professional and Consulting Services (workshops/trainings) through the Parent Institute of Quality Education to parents to increase parent engagement. Year 1: Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | July 2014 – June 2017 | Principal; APs; Dept. Chairs; Coordinators; Teachers; Parent Community Representative | Agendas; Council Sign-ins; Coffee w/Principal Sign-ins; School Newsletter; Parent Center; Calendar; Marque; Blackboard Connect Messages Purchase Order; Workshops; Contract; Sign-ins; Agendas
II-SIG 20: Ensure that the school receives ongoing, intensive technical assistance and related support from the LEA, the SEA, or a designated external lead partner organization (such as a school turnaround organization or an EMO).
| The LAUSD SIG Office will: 1) over see the implementation of the school plans; 2) provide resource and technical support throughout the grant, along with monitoring and overseeing the ongoing evaluation; 3) provide expert guidance and PD to support the curriculum and instruction, evaluate school performance against established SIG achievement goals 4) set benchmark data dates and gather and analyze report data 5) offer actionable recommendations for necessary changes and monitor the SIG budget implementation for each school. Year 1:Started Completed Year 2: Will continue Completed Year 3: Will continue |  |  | July 2014 – June 2017 | Chief, Division of Intensive Support and Intervention, SIG Director, LAUSD SIG Office, LEA Accountability Reports | LEA Accountability Reports, as determined by SIG. Agendas, sign-ins, school visit logs, communication (emails, website)
VI-SIG 30: Optional Component