## Los Angeles HS-Restart
SIG Form 10.3 - Restart Implementation Chart for a Tier I or Tier II School
LEA: | Los Angeles Unified School District | Date: May 20, 2016
School: | Los Angeles High School
Required Components | Strategies | Start & End Dates (MM/YYYY) | Oversight | Description of Evidence
Fulfill all California requirements for converting to a charter school (if applicable).
N/A | N/A | N/A | N/A | N/A
III-SIG 21: Create a locally-determined rigorous review process for the purposes of selecting a CMO or an EMO.
| The decision by LAUSD to allow California State University, Dominguez Hills (CSUDH), a nonprofit EMO, to support the school’s instructional program was made through a rigorous process of recruiting, screening and selecting Network Partners: • Demonstrated track record of support for teacher-leadership, student achievement, and capacity to design and manage high-quality school processes. • Business qualifications: track record and experience with school turnaround and transformation; depth and extent of local presence; relationships with community groups. • Personnel qualifications: background and professional qualifications of CSUDH staff. • Financial viability of organization. • Experience implementing school support strategies, including performance on prior school transformation efforts. CSUDH passed this review and became Network Partners. Year 1: Completed Year 2: Will continue Completed Year 3: Will continue | 08/2014 – 06/2017 | LAUSD, Office of Superintendent | • Qualitative data from LAUSD schools where CSUDH has partnered in school transformation • MOUs with schools and community partners • Staff bios and résumés • Evidence of school partnership success outcomes • Review of CSUDH philosophy and record of successful practice implementation
III-SIG 22: Create a plan to transfer students who either cannot attend the new school because their grade is no longer served by the Restart school or whose parents choose not to have their child attend the Restart school.
| The new Los Angeles High School will serve grades 9-12. All currently enrolled grades 9-11 in the attendance boundary of Los Angeles High School will be offered a place at the new Los Angeles High. If a family chooses not to send their child to the new school, they can ask LAUSD to create an “opt-out plan” for a place at another LAUSD school. Year 1 Completed. Year 1: Completed Year 2: Will continue Completed Year 3: Will continue | 07-2104 – 06/2017 |  | MOU between LAUSD and CSUDH
III-SIG 23: Create an accountability contract with the CMO or EMO which includes clearly defined goals for student achievement.
| The MOU between LAUSD and CSUDH acknowledges CSUDH’s accountability to the LAUSD Board of Education to support defined goal areas of the LAUSD Performance Meter, in addition to defined goals of Los Angeles High School. Annually, CSUDH will submit a report on the performance of the school to the LAUSD board and superintendent. If the school is not meeting its annual targets, CSUDH and LAUSD will work together to refine strategies as necessary. If the school does not substantially achieve the performance metrics in three years, the district and school can terminate the relationship with CSUDH. However, the superintendent can take action at any time if the academic situation requires more urgent attention. Year 1: Completed Year 2: Will continue Completed Year 3: Will continue | 07-2104 – 06/2017 | LAUSD, CSUDH Director | MOU between LAUSD and CSUDH
VI-SIG 30: Optional Component
II-SIG 14: Provide staff ongoing, high-quality, job-embedded professional development that is aligned with the school's comprehensive instructional program. | CSUDH will utilize resources and expertise that are elements of its Innovative School Leadership Initiative (ISLI) grant to work with groups and individual teachers and administrators in data analysis, lesson analysis, explicit direct instruction, and conflict management, among other areas, in support of teacher and leader development. Independent contractor Paula Evans will also utilize the Critical Friends Group protocols to support teacher growth. Administer stakeholder surveys to assess instructional effectiveness and challenge areas • Develop PD process (data analysis, need identification, instructional solution, implementation, assessment, data analysis..) that allows focused collaboration (involving common instructional areas) within PLC, department, grade-level interactions • Develop protocols for positive collaborative interactions using Critical Friends Group (CFG) protocols, including common planning time. • Develop outside partnerships, including Paula Evans’ Critical Friends Group and Loyola Marymount University’s Center for Math and Science Teaching (CMAST), to enhance current instructional focus areas • Conduct faculty study sessions during summer and semester breaks focused on developing interventions for underperforming students • Train all staff on protocols for data analysis • Conduct PD sessions focused on aligning increased expectation and rigor with effective classroom management strategies Year 1: Completed Year 3: Will continue Year 2: Additional funding for (1) PD for a 3 day team building and planning retreat (2) Cognitive Coaching Foundation to provide research- based training on the thinking and reflection processes that underlie instructional decisions (3) Summer PD for teachers to build capacity and provide resource for teachers of Korean Language (4) UCLA Writing Project to improve students' academic writing (5) Northwestern University Courses that will teach teachers to build capacity and train students in new career pathways focusing on the Arts and Museum studies (6) 6 counselors to train on data analysis and intervention program development. (7) collaborate with EMO to develop a Math and Science program to support enhanced instruction in math and science designed to focus on addresing underperforming subgroups at no charge. (8) PD for 2 day provided by Robert Evans ( 9) Collaborate with EMO to develop semester break study session (10) Attend AVID Institute for training - Fund up to 5 teachers per session to participate in 9 "Walk LA" Saturday PD sessions with local Arts Education Consultant, Bev Meyer, focusing on integrating community and art into common core curriculum. - Fund a one day Leadership Retreat for Administrators and the Instructional Leadership Team (ILT) to provide leadership training, team building and strategic planning geared toward improving student achievement. - Fund Professional Development Session for 36 teachers (2 days x 6 hours) with Bev Meyers on integrating seach and drama into the curriculum. Year 2: Completed | 07/2014 – 06/2017 | School Staff ISIC Superintendent School Community CSUDH | • Teaching and Learning Framework • TGDC Observation and Feedback • PD Agenda/Sign-In • Classroom Observation Reports • PLC/Collaboration Work Logs • Student Outcomes • Faculty study session minutes
II-SIG 17: Promote the continuous use of student data to inform and differentiate instruction in order to meet the academic needs of individual students. | • Coordinate with EMO on development of protocols for data analysis that are focused on student success • Create intervention teams that monitor student outcomes and develop intervention strategies for struggling students • Fund Problem Solving Data Coordinator to coordinate data analysis and train staff • Fund teacher time to monitor success of intervention/enrichment opportunities, modifying where data indicates • Fund and utilize instructional coaches in core areas to analyze data and support teachers in development of practices that meet the needs of all students Fund 5 hours/week of counselor Z-Time to perform focused data analysis and intervention program development for underperforming subgroups, notable Special Education, English Learner, and Socio-Economically Disadvantaged • Fund Instructional Specialist to develop and monitor instructional programs that support intervention and enrichment for all students • Fund clerical support to create data reports and general support to intervention programs Year 1: Completed Year 2: Will continue and add funding for (1) an Instructional Coach to assume activities of the Instructional Specialist (2) Intervention Data/technology Coordinator to provide data analysis in place of the Problem Solving Data Coordinator. (3) Half-time Intervention Support Coordinator to serve EL students, a targeted student population, as EL Coordinator. The coordinator will work with EL students and their families to address their unique needs (in the areas of specific language, academic and social-emotional needs) to improve overall student achievement. Coordinator will monitor data, assist with testing and work directly with students, teachers, counselors and admins to support and track EL students' progress. Year 2: Completed Year 3: Will continue | 07/2014 – 06/2017 | School Staff ISIC Superintendent School Community CSUDH | • LAUSD Performance Data • Grade-level matriculation rates • Graduation Data • Grade Data • CAHSEE Data • Student Attendance • Classroom Observation Logs • Counseling Logs • AP Data • Behavior/Suspension Data
II-SIG 18: Establish schedules and implement strategies that provide increased learning time. | Enrichment/Intervention: • Develop and fund 15 beyond the bell auxiliary periods, APEX credit recovery course, and summer school opportunities outside of the school day for students to receive support, including credit recovery and behavior interventions. Add funding for 1 admin. and 1 clerical to support Saturday intervention/credit recovery classes. - Year 3: Fund a full time math intervention teacher to offer math elective intervention classes embedded into the school day. •Fund college counselor to develop and monitor student graduation progress and college-readiness opportunities, and school psychologist to develop and monitor mental health programs and progress of students. • Fund intervention/enrichment program materials, including books and technology, in support of community partnerships (increase funding to provide adequate resources to support the many programs listed below) • Identify and create 6 auxiliary matrix support for specialized intervention, support, and college/career-pathway courses, including Advancement Via Individual Determination (AVID), Integrated Career Arts Pathway (ICAP), and robotics, with an emphasis on developing 21st Century skills in careers and technology, that are sequenced courses of study that progress each year for high-achieving students -Year 2-3 Implement and fund a Summer Bridge program and counselor to support the successful articulation of incoming students and program development for the first year of high school. • Identify technology intervention/enrichment opportunities, (i.e., ALEKS, Read 180, etc.) and fund software as appropriate to meet needs of students. Buy up to 1500 licenses for Achieve 300, Empower Pro, to provide accelerated literacy growth through differentiated instruction. • Fund technology coordinator(s) to support technology needs, including training teachers in the use of technology • Assess and fund hardware necessary to provide electronic access and intervention to struggling students, including laptops and carts • Fund the Institute for Student Empowerment, a nationally recognized program designed to assist economically challenged students gain deeper understanding of the value of education by helping them connect academics to their financial well-being (Year 1 only) • Fund additional hardware, 4 Laptop carts-one for each content area with 120 laptops (30 laptops for 1 cart) to provide electronic access and intervention for struggling students - Increase number of LCD projectors, document readers and laserjet printers to provide updated tools in all classrooms so teachers have necessary equipment on hand to provide exciting/differentiated lessons, and don't have to worry about securing equipment ahead of time. • Fund new desktop Apple computers in the Computer Learning Center and New PCs for the computer lab in room 150. Both labs provide students with access and training on both Apple and PC platforms core writing and critical thinking by providing a media center to support student learning at higher levels • Purchase of Attendance Recovery Software to support attendance improvement • Fund microcomputer technology support for summer school • Fund additional Microcomputer Tech support for school-wide technology needs, including online programs, computer labs and computer cart/laptops Year 1 - Completed Year 2 - will continue above and fund (1) an Intervention Enrichment teacher to provide support to economically challenged at risk students, higher level college bound students, and seniors at risk of not graduating during the school day (2) Fund 5 6 teaching assistants to support the teacher and provide direct service to students in the classroom (3) Fund additional Microcomputer Support Assistant to help with high demand for technical assistance and set up due to substantial increase in new computers and other technologies and a large percentage of seasoned teachers unfamiliar with technology. Collaboration: • Compensate teachers for 2 hours/month development time spent outside of regular school hours that are focused on analyzing data, modifying lessons, and monitoring instructional practice in alignment with the LAUSD Teaching and Learning Framework rubric and focus elements, and developing strategies for increasing rigor in the classroom. • Extra PD sessions of at least two hours per month focused on supporting all teachers develop strategies for increasing rigor in the classroom. • Provide compensation for activities outside of normal school day, including 7th period auxiliary classes, summer school, and summer bridge programs, among others, that support instructional success. - Fund after school AP enrichment geared towards placement exams - Fund 2 hrs/month for 2 lead teachers who will be trained to carry on the work of Paula Evans in facilitating the Critical Friends Group, helping to insure continuity and sustainability. Add 18 teachers back into after school meetings along with the 2 lead teachers. - Increase number of days for substitute release time as teachers have consistently asked to have more time to observe their peers, this will allow more opportunities for classroom visits both on campus and at other schools. - Fund teachers to provide after-school tutoring for students enrolled in their own classes, allowing for more personal, individualized instruction for their struggling students. -Fund teachers for providing After school tutoring, Credit Recovery , APEX classes and Enrichment classes -Fund tutoring for at-risk students to provide targeted intervention for seniors in all core areas preparing them for graduation -Fund enrichment training (AVID Advanced Placement) for teachers to fully support higher level college bound students -Fund any unspecified building teacher capacity in dealing with at-risk and EL students Professional Development workshops Fund an Intervention Coordinator for EL subgroup and testing responsibilities for ensuring that the EL subgroup makes adequate yearly progress and administrates state mandated and district mandated testing -Fund the expansion of the 9th grade summer bridge program from 4 weeks to 5 weeks and from 4 hours per day to 5 hours per day -Fund the expansion of the Credit recovery and intervention summer school program from 4 weeks to 5 weeks and from 4 hours per day to 5 hours per day. -Fund a counselor to support 9th grade summer bridge 5 week session. -Discontinue funding Parent Resource liaison as the position will be funded through other sources. Year 3: Will continue | 07/2014 – 06/2017 | School Staff ISIC Superintendent School Community CSUDH | Master Schedule, LAUSD Human Resources records, IMA orders and Invoices
II-SIG 19: Provide ongoing mechanisms for family and community engagement. | • Fund private contractor to make develop workshops, facilitate meetings, distribute newsletters, and coordinate other supplemental outreach to community and capitalize on school community history. The person hired for this position will network among parents and LA High administration, faculty, and staff. They will organize events – both social and informative in nature – to engage parents with our school. Our goal is that parent involvement will spread through the efforts of this hired position. Specific tasks include: creation of call sheets, prepare materials for all meetings, present information to help support parent understanding of the school’s instructional program as well as communicate to different stakeholders the availability of instructional resources to enhance student learning. • Fund community liaison responsible for coordinating and monitoring private contractor responsibilities, adjusting as needed for maximum efficacy • Identify and fund social supports, including, but not limited to: psychologist and College Counselor to monitor student success, including support for the underperforming subgroups of Special Education, English Learner, and Socio-Economically Disadvantaged students Year 1 Completed Year 2 - Fund an outside source, Parent Institute for Quality Education (PIQE) to provide parent engagement programs. Add funding to continue program into the second semester in order to continue the momentum and take parents to the next level of engagement. The targeted, but not sole, audience will be the parents of 9th graders, capturing them at the beginning of the high school journey will help keep them actively engaged in supporting their students throughout high school. -Fund an additional day to the existing 4 days per week for the school psychologist who develops and mental health programs and progress of the students -Fund a psychiatric social worker provide services to support the non-academic needs of students Year 2: Will continue Completed Year 3: Will Continue | 07/2014 – 06/2017 | School Staff School Community CSUDH | • Parent participation logs • Parent meeting agendas • Meeting/community flyers
II-SIG 20: Ensure that the school receives ongoing, intensive technical assistance and related support from the LEA, the SEA, or a designated external lead partner organization (such as a school turnaround organization or an EMO). | The LAUSD SIG Office will: 1) oversee the implementation of the school plans; 2) provide resource and technical support throughout the grant, along with monitoring and overseeing the ongoing evaluation; 3) provide expert guidance and PD to support the curriculum and instruction, evaluate school performance against established SIG achievement goals; 4) set benchmark data dates and gather and analyze report data; 5) offer actionable recommendations for necessary changes and monitor the SIG budget implementation for each school. Year 1: Completed Year 2: Will continue Completed Year 3: Will continue | 7/14-6/17 | Chief of Intensive Support and Intervention, SIG Office Staff | Agendas, sign-ins, school visit logs, communication (emails, website)