## San Fernando HS-Restart (hidden)
SIG Form 10.3 - Restart Implementation Chart for a Tier I or Tier II School
LEA: | Los Angeles Unified School District | Date: March 8, 2014
School: | San Fernando High School
Required Components | Strategies | Start & End Dates (MM/YYYY) | Oversight | Description of Evidence
Fulfill all California requirements for converting to a charter school (if applicable).
N/A | N/A | N/A | N/A | N/A
II-SIG 21: Create a locally-determined rigorous review process for the purposes of selecting a CMO or an EMO.
| The decision by LAUSD to allow Los Angeles Education Partnership (LAEP), a nonprofit EMO, to support the school’s instructional program was made through a rigorous process of recruiting, screening and selecting Network Partners and according to the following criteria: • Demonstrated track record of student achievement and capacity to design and manage a high-quality school. • Business qualifications: years as a nonprofit EMO; track record and experience with public school turnaround and transformation; depth and extent of local presence; relationships with community groups. • Personnel qualifications: background and professional qualifications of LAEP staff. • Financial viability of organization. • Experience implementing instructional strategies; performance on prior school transformation efforts. LAEP passed this review and became a Network Partner | 7/14 - 6/17 | LAUSD Office of Superintendent | Performance data from LAUSD schools where LAEP has partnered in school transformation MOUs with schools and community partners Staff bios and résumés LAEP financial statements LAEP articles of incorporation, bylaws, IRS determination letter
II-SIG 22: Create a plan to transfer students who either cannot attend the new school because their grade is no longer served by the Restart school or whose parents choose not to have their child attend the Restart school.
| The new San Fernando High School will continue to serve grades 9-12. All currently enrolled students will be offered a place at the new San Fernando High School. Incoming 9th grade students will utilize the Zone of Choice process, as required by LAUSD. If a family chooses not to send their child to San Fernando High School, they can ask LAUSD for an opt-out plan for a place at another LAUSD school. | 7/14-6/17 | LAUSD School Administration LAEP Project Coordinator LAEP Transformation Facilitator | School enrollment records Parent requests for opt-out plans Evidence of submitted opt-out plans
II-SIG 23: Create an accountability contract with the CMO or EMO which includes clearly defined goals for student achievement.
| LAUSD Board of Education to meet the defined five goal areas of the LAUSD Performance Meter. Annually, LAEP will submit a report on the performance of the school to the LAUSD board and superintendent. If the school is not meeting its annual targets, LAEP and LAUSD will work together to alter strategies as necessary. If the school does not substantially achieve the performance metrics in three years, the district and school can terminate the relationship with LAEP. | 7/14-6/17 | LAUSD LAEP President LAEP CEO | MOU between LAUSD and LAEP
VI-SIG 30: Optional Component
II-SIG 14: Provide staff ongoing, high-quality, job-embedded professional development that is aligned with the school's comprehensive instructional program.
II-SIG 14 | Each teacher and school leader will develop an Individual Growth Plan/Reflection Portfolio consistent with the LAUSD Teacher and Learning Framework. Subject-specific and school-wide Professional Development (PD) will be developed based on common goal areas related to teacher and school leader Individual Growth Plans (IGP). PD topics will include: unit development, lesson study, instructional rounds, growth toward school-wide interdisciplinary lessons, calibration of student work, rigor and relevance, pacing plans aligned to interdisciplinary units, SDAIE PD and co-teaching PD for Special Education and General Education teachers. Prior to the beginning of each school year, faculty votes on whether to extend unpaid PD time for the following school year, based on the following data: student needs/performance on standardized assessments, student grades, and individual growth plans. We have received waivers from UTLA and LAUSD in order to extend unpaid PD. The unpaid PD will be used for the creation of interdisciplinary units and lesson plans, integrating the theme of each Academy, project-based learning, and the Common Core. This prepares our students for Career/College Pathways. Subject-specific Advanced Placement (AP) training for teachers interested in teaching AP courses. English Language Arts (ELA) Professional Development time will be spent on revising instructional strategies, which will then be modeled and tested on select student groups. These PD sessions will be designed by the department chairpersons and members of the Vertical Alignment Committee. Teachers will meet on a weekly basis after school to ensure that the particulars of the plan are well understood and can be successfully implemented. In the immediate future, these strategies will be shared and implemented school-wide. Math PD will focus on rigorous instruction and SDAIE strategies to support student needs. Implementation and progress will be monitored through peer classroom observations and lesson study. | 7/14-6/17 | ISIC Instructional Director Principal Administration School Staff LAEP Transformation Facilitator ELA Dept Chair Math Dept Chair Math Coach | Individual Growth Plans Teaching and Learning Framework Professional Development Agendas Sign-in logs Training Certificates Master Schedule Conference Attendance forms and logs Student scores on in-house assessments designed to measure the effectiveness of revised ELA plans Math intervention curriculum ELA intervention curriculum Vertical Alignment Committee agendas Teacher logs
II-SIG 15: Give the school sufficient operational flexibility (such as staffing, calendars/time, and budgeting) to implement fully a comprehensive approach to substantially improve student achievement outcomes and increase high school graduation rates.
II-SIG 15 | Create at minimum one complete cohort of teachers and students within each of our three themed Academies and our Ninth Grade House during the first year of implementation and increase the number of cohorts each year by adjusting the Master Schedule. Our current daily Bell Schedule provides increased learning time by 8.6 days annually. We will re-prioritize our school budgets to continue to support intervention, credit recovery, and Professional Development. | 7/14-6/17 | ISIC Instructional Director Principal Administration Leadership Team LAEP Senior Director | Agendas Sign in logs Evidence of decisions made re staffing, calendars and budgeting Master Schedule Student logs Student grades Bell Schedule
II-SIG 17: Promote the continuous use of student data to inform and differentiate instruction in order to meet the academic needs of individual students.
II-SIG 17 | San Fernando High School staff and our EMO will continuously use data to improve student achievement including graduation rates, proficiency rates on state assessments, attendance rates, and college/career readiness. We will create an Intervention Team comprised of the LAEP Transformation Facilitator, Learning Support Coordinator, Intervention Support Coordinator, PSA Counselor, Intervention Teachers (English and Math), Special Education Teachers, English Learners Teachers, and parents to meet regularly in order to ensure that the specific learning needs of our at-risk students are being met. The Intervention Team will analyze key data systems on a weekly basis to monitor progress of student achievement. Our goal is to increase the percentage of students who pass their classes with a C or better to meet the A-G requirements. The Intervention Support Coordinator and the LAEP Transformation Facilitator will be responsible for recommending interventions and developing targeted instruction. Common planning time, professional development and constructive feedback from classroom observations will allow for adjustment of instruction to meet the academic needs of individual students. | 7/14-6/17 | Principal Administration Department Chairs Lead Teachers LAEP Transformation Facilitator | LAUSD's Performance Meter of Student Achievement: Graduation Rate, Proficiency for all on Common Core assessments and CAHSEE, Attendance Rate, Parent and Community Engagement, and School Safety Meeting Documentation: Agendas, Sign in logs Home visit logs Counseling logs SARB/SART logs Summer School Student Rosters CAHSEE pass rates Student grades
II-SIG 17 | Intervention English and Math Teachers will teach recovery classes to at-risk students to better maintain a direct path in meeting graduation requirements. Data, including student grades, Performance Assessment Task results, Individualized Education Programs (IEPs) and formative and summative assessments indicate a need for intervention classes in English and Math. Smartboards and LCD projectors to facilitate student learning in recovery classes and enrichment classes. Intervention Materials--Composition notebooks for the support of English and Math intervention classes, Summer School and Summer Bridge program. Student planners for the support of our new organizational skill-building program for all students emphasizing study habits, monitoring pertinent dates, attendance, homework, etc. Poster boards, manipulatives, CDs, DVDs, media for the support of English and Math intervention classes, Summer School and Summer Bridge program. Microcomputer Support Assistant (MCSA) to directly support the technology needs of our intervention teachers and students (e.g., use of on-line recovery program, effective use of Smartboards and Revolution program). | 7/14-6/17 | Administration Intervention and Support Coordinator Intervention Counselor Admin in charge of Technology | Master Schedule Student work Student grades Classroom observations Stulls Work logs
II-SIG 17 | Intervention Support Coordinator will focus on monitoring and increasing student academic achievement of Special Ed students, as measured by student grades and state assessment scores. Revolution Prep to support struggling students in ELA, Algebra, Geometry and for CAHSEE preparedness Desktop computers and a high capacity printer for student use in the library so that students are able to access the Revolution Prep program and on-line learning for credit recovery, before school and after school. | 7/14-6/17 | Principal Administration Department Chairs Lead Teachers LAEP Transformation Facilitator | LAUSD's Performance Meter of Student Achievement: Graduation Rate, Proficiency for all on Common Core assessments and CAHSEE, Attendance Rate, Parent and Community Engagement, and School Safety Meeting Documentation: Agendas, Sign in logs SARB/SART logs Student grades IEPs Student interview logs Assignment of Revolution Prep and on-line learning licenses
II-SIG 17 | 9th grade test results will be used to determine how well Exposition, Persuasion, and Literacy Analysis components of ELA 9th grade pacing plan align with CCSS; 10th grade test results will be used to determine how successful ELA 10th grade pacing plan is in building upon skills acquired in 9th grade; 11th grade test results will be used to determine how well the 11th grade pacing plan does in further developing the skills and knowledge acquired in the previous two grades. They will also be used to determine how well the plan prepares students for the composition of more complex essays on the CCSS exam. Our school currently has an effective math tutorial program, as evidenced by an improvement of student math skills. There is a need to expand our math tutorial program to serve an additional segment of our at-risk student population. | 7/14--6/17 | Principal Administration ELA Dept Chair Math Dept Chair Math Coach LAEP Transformation Facilitator | Statistical breakdown of student scores Periodic Assessments Student math scores on formative and summative in-class assessments Student grades
II-SIG 17 | Given how well this year's 9th and 10th grade students performed on the first English Language Arts CCSS-aligned Periodic Assessment and how similar the Performance Task section of the CCSS test for 11th graders is to sections of our pacing plan, we will adapt our vertically aligned pacing plan as opposed to jettisoning it. When we engage in that process, we will continue to be mindful of the higher levels of Bloom's Taxonomy; quadrants B & D of the Rigor/Relevance Framework developed by the International Center for Leadership in Education; and "Academic Literacy" as defined by the Intersegmental Committee of the Academic Senates of the California Community Colleges, the California State University, and the University of California--in addition to the Common Core State Standards. As per data analysis, we need to expand our current 9th grade math tutorial program and our 9th grade English intervention courses to serve a larger population of at-risk students. | 7/14-6/17 | Principal Administrators ELA Dept Chair Math Dept Chair Math Coach LAEP Transformation Facilitator | Hard and digital versions of revised, vertically aligned ELA pacing plans Math intervention curriculum English intervention curriculum Master Schedule
II-SIG 18: Establish schedules and implement strategies that provide increased learning time.
II-SIG 18 | Increased learning time (ILT) will be available to all students during a 0 and 7th period for credit recovery and/or enrichment, utilizing the Edgenuity online program as well as dual enrollment college classes and enrichment autoshop and graphic arts classes. Summer Bridge Program for incoming 9th grade students (and their parents) who have low state assessment scores or earned an F in their ELA or math class. Will provide instructional intervention in English Language Arts and math for at-risk students transitioning from middle school to high school. Students will be able to familiarize themselves with the campus, staff, expectations, and school policies. Students will attend a study skills seminar and access social development support, as needed. Summer School will provide standards-based instruction for credit recovery and enrichment for students in grades 9-12, enrolled at San Fernando High School. Includes clerical, custodial and campus aide support. Common planning time is built into our Master Schedule so that cohorts of teachers will share a common conference period in order to facilitate collaboration between grade-level and subject-specific teachers. Common planning time will facilitate interdisciplinary collaboration specific to grade level. | 7/14-6/17 | Administration Leadership Team LEAP Transformation Facilitator | Master Schedule Roster of students attending 0, 7 period classes Roster of students attending Summer Bridge attendance rosters Summer School attendance rosters Summer School grades
II-SIG 18 | Additional Advanced Placement (AP) courses will be offered to all students. These enhanced classes will better prepare our students for college work. Enrichment Culinary Arts teacher (ROP/LAUSD authorized) and supplies, materials, consumables, ingredients for the re-instatement of our Culinary Arts program. This program, eliminated approximately three years ago due to RIFs, was a major "feeder program" to the post-secondary Culinary Arts program at our local Mission Community College. We have a fully functional professional kitchen/culinary arts classroom. Enrichment Computer Teacher to provide students with computer concepts, programming, web design and film editing classes to enhance the Engineering and Design Career Pathways. | 7/14-6/17 | Administration Head Counselor Department Chairpersons Lead Teachers | Master Schedule Teacher Lesson Plans Student Work Attendance Rosters Student grades
II-SIG 19: Provide ongoing mechanisms for family and community engagement.
II-SIG 19 | Pupil Services and Attendance Counselor (PSA) will assist in reducing student absenteeism, truancy and transiency rates while promoting dropout prevention and student recovery. Intervention Counselor will regularly monitor the academic progress of a select group of at-risk students (based on specific academic criteria, including grades) so that they successfully complete A-G requirements and matriculate to the next grade level. The Community School Coordinator (funded by a community partner) and administrator overseeing Community Partnerships will act as primary liaisons for new and continuing partners. Community members and staff will share information and advocate when appropriate via: o Resource Council o SFNP Newsletter o SFNP Monthly Calendar o SFHS Website and student announcements Students will be provided with leadership and volunteer opportunities with Community Partners. Working with Title 1 and the Community School Coordinator, multiple agencies will provide ongoing parenting, parent engagement, and school readiness workshops. Health & Wellness Coordinator (funded by a community partner) and Medical Science Academy will host Annual Student Health Fair, open to all students and community health organizations. Partners and school staff will provide student-led Family Orientation for incoming students. | 7/14-6/17 | Administration Community Representative LAEP Community School Coordinator | Parent meeting logs Home visit logs Counseling logs Student Interview logs IEPs Meeting agendas Meeting minutes Attendance logs SFNP Newsletter SFNP Monthly Calendar SFHS Website
II-SIG 20: Ensure that the school receives ongoing, intensive technical assistance and related support from the LEA, the SEA, or a designated external lead partner organization (such as a school turnaround organization or an EMO).
II-SIG 20 | The LAUSD SIG Office will: 1) oversee the implementation of the school plans; 2) provide resource and technical support throughout the grant, along with monitoring and overseeing the ongoing evaluation; 3) provide expert guidance and PD to support the curriculum and instruction, evaluate school performance against established SIG achievement goals; 4) set benchmark data dates and gather and analyze report data; 5) offer actionable recommendations for necessary changes and monitor the SIG budget implementation for each school. | 7/14-6/17 | Chief, Division of Intensive Support and Intervention SIG Office | Agendas, sign-ins, school visit logs, communication (emails, website)
I-SIG 09: Provide appropriate social-emotional and community-oriented services and supports for students.
I-SIG 9 | As a Community School, SFHS is committed to serving the social-emotional, academic, leadership, and community needs of students by: 1) Partnering with quality, effective community agencies to assist the school in identifying needed services for students, such as the ACE program (Achievement and Commitment to Excellence), funded by a community partner. 2) Coordinating these services collaboratively under the leadership of LAEP and a community school coordinator. 3) Continue working with current successful partners to support ongoing grants and funding. 4) Engaging youth leadership development and ensuring that all students have access to mindful leadership opportunities both on and off campus. 5) Networking with new or current agencies to meet the demands of identified student needs. A Career/College Counselor will align business partners with our themed Academies, facilitate career related activities, conduct resume writing workshops, arrange for and monitor student internships, conduct portfolio checks, college workshops, mock interviews, and organize a school-wide Career and College Day. Campus aides will improve the overall safety, culture and climate of the school, including an increase of in-class attendance. | 7/14-6/17 | Administration LAEP Community School Coordinator Deans Head Counselor | Agendas of Community Partner meetings Sign-in logs Evidence of student participation in socio-emotional/community-oriented programs Schedule of career/college activities and student rosters Work schedules Parent Surveys Student Surveys

## San Fernando SH Narrative
CA Dept of Education
Cohort 3 SIG Program |  |  | Please color all changes within your narratives.
School Name: San Fernando Senior High School
School Budget Narrative
Component Number | Activity Description | SIG Funds Budgeted | [9 empty] | Object Code
(Identified per year)
|  | Pre-Imp | FY 2014-15 Original Budget | FY 2014-15 Budget Changes Feb 2016 |  | FY 2015-16 Original Budget | FY 2015-16 Budget Changes Q3 - Feb 2016 | FY 2015-16 Budget Changes Sept 2016 | FY 2016-17 Original Budget | FY 2016-17 Budget Changes Q3 - Feb 2016 | FY 2016-17 Budget Changes Q1 - Sept 2016
II-SIG 19 | Intervention Counselor will regularly monitor the academic progress of a select group of at-risk students. |  | 72592 | 76796.23 |  | 72592 | 80053 | 80301.81 | 72592 | 80418 | 81561 | 1200
II-SIG 19 | Pupil Services and Attendance Counselor (PSA) will assist in reducing absenteeism, truancy and transiency rates while promoting dropout prevention and student recovery. |  | 77426 | 64281.42 |  | 77426 | 70848 | 70915.64 | 77426 | 74806 | 75546 | 1200
II-SIG 9 | Counselor, 9th grade--will provide counseling services for early identification for barriers to academic achievement of students and will develop student knowledge, skills and attitudes that promote personal, social, emotional and academic growth. Counselor will participate in SSPT and parent education workshops. |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 80117 | 1200
I-SIG 9 | Career/College Counselor to facilitate career related activities, including work experience, linked learning and college workshops to all students. |  | 72592 | 80029.96 |  | 72592 | 82616 | 83279.75 | 72592 | 82616 | 83434 | 1200
II-SIG 18 | ROP/LAUSD Authorized Culinary Arts Teacher--will provide enrichment culinary arts classes to students in our pre-existing kitchen classroom. |  | 72592 | 56198.65 |  | 72592 | 60119 | 67319.77 | 72592 | 62896 | 63518 | 1100
II-SIG 17 II-SIG 18 | Two Intervention Math Teachers to teach intervention math tutorial classes and recovery classes to at-risk students so that students are able to meet A-G requirements. |  | 145184 | 104234.93 |  | 145184 | 125094 | 114080.02 | 145184 | 130849 | 132143 | 1100
II-SIG 17 II-SIG 18 | Two Intervention English Language Arts Teachers to teach intervention ELA classes and recovery classes to at-risk students so that students are able to meet A-G requirements. |  | 145184 | 117099.34 |  | 145184 | 132350 | 123396.78 | 145184 | 138978 | 140353 | 1100
II-SIG 18 | Enrichment Computer Teacher to teach computer concepts, programming, web design and film editing to enhance the Engineering and Design Career Pathways. |  | 72592 | 80029.96 |  | 72592 | 82616 | 83852.64 | 72592 | 82616 | 83434 | 1100
II-SIG 17 | Intervention Support Coordinator will support our Special Education students (11%). The coordinator will focus on monitoring and increasing student academic achievement of Special Ed students, as measured by students grades and state assessment scores. |  | 72592 | 61695.22 |  | 72592 | 62470 | 63299.53 | 72592 | 66228 | 66883 | 1900
II-SIG 14 | PD X-Time: All teachers, counselors and coordinators will attend 24 hours of professional development based on common goal areas, including Individual Growth Plan/Reflection Portfolio, common unit development, lesson study, interdisciplinary lessons, instructional rounds, calibration of student work, SDIAE and Special Ed/General Ed co-teaching model. (110x1423.2=$156,552) Year 1: ~75 staff x 30 hrs, ~80 staff x 11 hrs Year 2: 121 staff x 30 hrs x $65/hr = $235,950 Year 3: 121 staff x 31 hrs x $65/hr = $243,815 |  | 156552 | 179520.45 |  | 195690 | 235950 | 134802 | 215259 | 243815 | 243815 | 1100 1200 1300 1900
II-SIG 18 | AP Auxiliaries to teach 4 additional AP courses, offered to all students. $59.30/hr x 80 hrsX4=$18,976x2=$37,952. Year 1: 2 AP courses only. Years 2-3: $65/hr x 80 hrs x 2 classes= $10,400 x 2 = $20,800 |  | 37952 | 17656.71 |  | 37952 | 20800 | 10344.66 | 47440 | 20800 | 20800 | 1100
II-SIG 18 | 3 Auxiliaries--2 Social Studies Auxiliaries, 1 Biology Auxiliary for Year 3. Offered to all students to ensure that all students complete A-G courses. $8,966 ($7,674 salary, $1,292 benefits) per semester x 2 = $17,932 x 3 auxiliaries = $53,796 ($46,044 salary, $7,752 benefits) |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 46044 | 1100
II-SIG 18 | Summer School--Standards based instruction for credit recovery and enrichment for students in grades 9-12; 5 hours a day for 24 days, 10 classes total (60 hrs. each class). 5 teachers x 120hrs x $59.30/hr=$35,580. Year 1: summer 2014 funded thru Core Waiver Years 2-3: 5 teachers x 120 hrs x $65/hr = $39,000 |  | 35580 | 10117.53 |  | 35580 | 39000 | 9270.72 | 35580 | 39000 | 39000 | 1100
II-SIG 18 | Summer Bridge Program to provide instructional intervention to at risk students transitioning from middle school to high school in Math and English Language Arts. 4 weeks, 3 hours a day. 4 teachers @$59.30/hr=$14,232. Year 1: summer 2014 funded thru Core Waiver Years 2-3: 4 teachers x 60 hrs x $65/hr = $15,600 |  | 14232 | 0 |  | 14232 | 15600 | 0 | 14232 | 15600 | 15600 | 1100
II-SIG 18 | 0 and 7th period for enrichment classes, 3 teachers: autoshop, graphic arts, credit recovery teacher for Edgenuity on-line program. 60 hours @ 59.30x3=$10,674. Year 1: Spring Semester only. Year 2: 5 Enrichment classes: Video Production, Cabinetry, Willwork & Woodwork; World of Music; Web Development & Production--5 teachers x 60 hrs x $65/hr x 2 semesters = $39,000 Year 3: 3 teachers x 60 hrs x $65/hr x 2 semesters = $23,400 |  | 10674 | 9375.11 |  | 21348 | 39000 | 18431.03 | 21348 | 23400 | 23400 | 1100
|  | 0 | 985744 | 857035.51 |  | 1035556 | 1046516 | 859294.35 | 1064613 | 1062022 | 1195648 | 1000-1999
II-SIG 17 | Microcomputer Support Assistant--will provide direct technology-related assistance to our intervention and enrichment teachers and students. |  | 38956 | 27801.95 |  | 38956 | 34422 | 33665.8 | 38956 | 36357 | 37266 | 2400
I-SIG 9 | Campus Aides Four 3-hour positions to improve the overall safety, culture and climate of the school, including an increase in in-class attendance. |  | 36752 | 27090.97 |  | 36752 | 32484 | 28729.64 | 36752 | 34356 | 39192 | 2900
II-SIG 18 | Summer School- clerical, custodial and campus aide support for the program; 60 hours for clerical@$30=$1,800. 60 hrs custodial@$30=$1,800; 60 hrs campus aide@$15.01=900 Year 1: Summer 2015 - 34 hrs custodial overtime |  | 4500 | 1020.49 |  | 4500 | 4500 | 1302.73 | 4500 | 4500 | 4500 | 2200 2400 2900
| 2000 Series Totals | 0 | 80208 | 55913.41 | 0 | 80208 | 71406 | 63698.17 | 80208 | 75213 | 80958 | 2000-2999
II-SIG 19 | Intervention Counselor |  | 26362 | 27592.65 |  | 26362 | 28970 | 30756.43 | 26362 | 30077 | 32856 | 3101 3201 3301 3401 3501 3601
II-SIG 19 | Pupil Services and Attendance Counselor (PSA) |  | 26975 | 23089.17 |  | 26975 | 27567 | 29216.52 | 26975 | 29222 | 31843 | 3101 3201 3301 3401 3501 3601
II-SIG 9 | Counselor - 9th Grade |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 32612 | 3101 3201 3301 3401 3501 3601
I-SIG 9 | Career/College Counselor |  | 26362 | 28097.53 |  | 26362 | 29361 | 31222.66 | 26362 | 30413 | 33172 | 3101 3201 3301 3401 3501 3601
II-SIG 18 | ROP/LAUSD Authorized Culinary Arts Teacher |  | 26362 | 25040.03 |  | 26364 | 25932 | 28311.61 | 26364 | 27408 | 29819 | 3101 3201 3301 3401 3501 3601
II-SIG 17 II-SIG 18 | Two Intervention Math Teachers |  | 52724 | 45573.25 |  | 52728 | 52605 | 51323.4 | 52728 | 55586 | 60497 | 3101 3201 3301 3401 3501 3601
II-SIG 17 II-SIG 18 | Two Intervention English Language Arts Teachers |  | 52724 | 44687.56 |  | 52728 | 53710 | 52576.93 | 52728 | 56825 | 61880 | 3101 3201 3301 3401 3501 3601
II-SIG 18 | Enrichment Computer Teacher |  | 26362 | 28112.23 |  | 26364 | 29361 | 32026.07 | 26364 | 30413 | 33172 | 3101 3201 3301 3401 3501 3601
II-SIG 17 | Intervention Support Coordinator |  | 26362 | 24922.53 |  | 26362 | 26291 | 28056.69 | 26362 | 27916 | 30385 | 3101 3201 3301 3401 3501 3601
II-SIG 17 | Microcomputer Support Assistant |  | 26167 | 15804.38 |  | 26167 | 24538 | 25570.77 | 26167 | 26027 | 28197 | 3102 3202 3302 3402 3502 3602
I-SIG 9 | Campus Aides |  | 5308 | 2638.71 |  | 5308 | 4704 | 2348.65 | 5308 | 4980 | 5580 | 3102 3202 3302 3402 3502 3602
II-SIG 14 | PD X-Time |  | 19898 | 28773.64 |  | 24255 | 35959 | 18977.64 | 27359 | 37157 | 41071 | 3101 3201 3301 3401 3501 3601
II-SIG 18 | AP Auxiliaries |  | 4824 | 2673 |  | 4824 | 3170 | 1765.36 | 6030 | 3170 | 3504 | 3101 3201 3301 3401 3501 3601
II-SIG 18 | Auxiliaries |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7752 | 3101 3201 3301 3401 3501 3601
II-SIG 18 | Summer School |  | 4522 | 1505.49 |  | 4522 | 5944 | 1885.78 | 4522 | 5944 | 6570 | 3101 3201 3301 3401 3501 3601
II-SIG 18 | Summer School- clerical, custodial and campus aide |  | 649 | 179.92 |  | 649 | 1016 | 265.21 | 389 | 1016 | 1096 | 3102 3202 3302 3402 3502 3602
II-SIG 18 | Summer Bridge Program |  | 1809 | 0 |  | 1809 | 2378 | 0 | 1809 | 2378 | 2628 | 3101 3201 3301 3401 3501 3601
II-SIG 18 | 0 and 7th period for enrichment classes |  | 1357 | 1394.16 |  | 2682 | 5944 | 2085.69 | 2713 | 3566 | 3942 | 3101 3201 3301 3401 3501 3601
| 3000 Series Totals | 0 | 328767 | 300084.25 |  | 334461 | 357450 | 336389.41 | 338542 | 372098 | 446576 | 3000-3999
II-SIG 18 | Supplies, materials, ingredients for student use as part of the culinary arts classes |  | 5000 | 4424.11 |  | 5000 | 5000 | 523.21 | 5000 | 5000 | 5000 | 4300
II-SIG 18 | Supplemental consumable instructional materials for fine arts and CTE classes will allow students to further engage in project-based learning. |  | 0 | 0 |  | 0 | 4087.93 | 2948.71 | 0 | 2000 | 10926.46 | 4300
II-SIG 17 II-SIG 18 | Revolution Program to support struggling students in ELA, Algebra, Geometry and CAHSEE Prep ($50x200=$10,000) Year 2-3: to support Common Core Prep instead of CAHSEE Prep |  | 10000 | 9986.67 |  | 10000 | 10000 | 10000 | 15000 | 10000 | 10000 | 4300
II-SIG 17 | Intervention Materials--composition books for the support of our Math and English Intervention classes, Summer School and Summer Bridge program. |  | 5000 | 7237.72 |  | 5590 | 10000 | 985.42 | 0 | 0 | 0 | 4300
II-SIG 17 | Intervention Materials--student planners for the support of our new school-wide program to teach organizational skills to our students, including study habits, monitoring of pertinent dates, attendance, homework, etc. |  | 5830 | 5856.44 |  | 5000 | 8000 | 7998.13 | 2892 | 8000 | 8000 | 4300
II-SIG 17 | Intervention Materials--poster boards, manipulatives, CDs, DVDs, media for the support of our Math and English intervention classes, Summer School program, Summer Bridge program. |  | 4756 | 1286.81 |  | 4740 | 10000 | 14572.79 | 0 | 1948 | 1948 | 4300
II-SIG 17 | 10 Smartboards for the support of student engagement in our Math and English intervention classes, AP classes, Culinary Arts classes, Enrichment Drama classes and Enrichment Computer classes. (10x$5,000=$50,000). Year 1: bought 8 smartboards Year 2: $5,719.88 x 8 = $45,759.04 |  | 50000 | 43172.08 |  | 0 | 45760 | 46383.66 | 0 | 0 | 0 | 4400
II-SIG 17 | LCD projectors for the technology support of our Math and English intervention classes, AP classes, Culinary Arts classes, Enrichment Drama classes and Enrichment Computer classes. ($1,000x10=$10,000). Year 1: bought 11 projectors. Year 2: $1,520.96 x 30 = $45,628.8 |  | 10000 | 17494.83 |  | 0 | 45629 | 43481.76 | 0 | 0 | 0 | 4400
II-SIG 17 | 2 Laptop carts with 30 laptops each to support the use of technology in classroom instruction; including the use of SmartPrep, SmartCity, KhanAcademy, Scholastic Reading Inventory, and turnitin.com. 2 carts x 1,966.37 = $3,932.74; 60 laptops x $1,210.69 =$76,574.14 |  | 0 | 0 |  | 0 | 76575 | 68813.6 | 0 | 0 | 0 | 4400
II-SIG 17 | 10 desktop computers and a high capacity printer for student use in the Library so that students are able to access the Revolution Prep program and on-line learning for credit recovery, before school and after school. (10x$1,200=$12,000 and 1x$1,000=$1,000) Printer - $1,520.96 |  | 13000 | 12203.11 |  | 0 | 1521 | 1903.98 | 0 | 0 | 0 | 4400
II-SIG 17 | 17 desktop computers for student use in the Library so that students are able to access the Revolution Prep program and on-line learning for credit recovery, before school and after school. (1,210.69x17=$20,581.73), 1 Printer - $1,600 |  | 0 | 0 |  | 20400 | 22182 | 20260.92 | 0 | 0 | 0 | 4400
II-SIG 17 | 17 desktop computers to be placed in our computer lab. Teachers bring students to the computer lab during class time so that students are able to complete projects that require on-line accessibilty, to complete interim assessments and to access SmartPrep and Smart City for SBAC math preparation. ($1,024.19X17=$17,411.23) |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 17411.23 | 4400
| 4000 Series Totals | 0 | 103586 | 101661.77 |  | 50730 | 238754.93 | 217872.18 | 22892 | 26948 | 53285.69 | 4000-4999
II-SIG 14 | AP Training for teachers, to increase AP course offerings for students. ($7,950 each teacher, including conference registration, hotel, per diem) |  | 7950 | 3921.81 |  | 5300 | 5300 | 2887.63 | 0 | 0 | 0 | 5200
II-SIG 21 | Los Angeles Education Partnership (LAEP) EMO to support the school's instructional program. |  | 300000 | 300000 |  | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 5800
| 5000 Series Totals | 0 | 307950 | 303921.81 |  | 305300 | 305300 | 302887.63 | 300000 | 300000 | 300000 | 5000-5999
| 6000 Series Totals | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6000-6999
| 1000 - 6000 Budget Subtotals | 0 | 1806255 | 1618616.75 |  | 1806255 | 2019426.93 | 1780141.74 | 1806255 | 1836281 | 2076467.69
| Indirect Rate - Year 1: 5.19%, Year 2: 3.86%, Year 3: 3.47% |  | 93745 | 84006.32 |  | 93745 | 77950 | 68713.5 | 93745 | 63719 | 72054 | 7310
| 7000 Series Totals | 0 | 93745 | 84006.32 |  | 93745 | 77950 | 68713.5 | 93745 | 63719 | 72054 | 7310/7350
| Totals |  | 1900000 | 1702623.07 |  | 1900000 | 2097376.93 | 1848855.24 | 1900000 | 1900000 | 2148521.69
|  |  | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | actual exp | 1702623.07 |  |  | actual exp | 1848855.24 |  | carryover | 248521.69
[10 empty] | year 3 award | 1900000
|  |  |  | 0 |  |  |  | 0 |  | total year 3 budget | 2148521.69
[10 empty] | difference | 0